## Proposed Timeline
Scenic Roads Protection and Preservation Bylaw
2020-11-02
Week → | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Phase I: Research
A. Research other Towns' best practices
B. Gain input from other towns' planners
Phase II: Develop Scenic Roads Blyaw Details
A. Chapter 90 Scenic Roads - edit
1.Purpose
2. PB shal take into consideration…
3. Update Definitions
a. cutting of trees
b. repair, maintenance, destrution of stone walls
B. Add a new Design Standards section
1. Research and develop a consistent driveway cut standard
C. Scenic Road Consent 133-37 - edit
D. Scenic Roads Application and Checklist - edit
Phase IV: Outreach & Explanation
A. Develop Outreach Materials
B. Conduct Outreach Meetings
1. Board and Committee Meetings (HCT, HHS, COA, etc)
2. General Public
C. Develop and Manage PR
1. Harvard Press/NextDoor
D. Public Hearings (Planning Board)
Phase V: Pass Bylaw
Town Meeting Prep and Town Meeting
NOVEMBER
DECEMBER
JANUARY
FEBRUARY
MARCH
APRIL
MAY

## Original
|  |  |  | Town of Harvard |  | 2020-10-27
Senior Residential Bylaw Timeline
| 2020 |  |  | 2021
| October | November | December | January | February | March | April | May
Kick-off /Launch- Redraft Process - Harvard Press
Phase I Reflection & Visioning
A. Reflect
1. Identify +/- of process, creation of bylaw
2. Develop & Share Lessons Learned for future bylaws
B. Vision
1. Develop Postits
2. Prepare Individual visions
C. Share Merged =/-'s, visions at 11/16 Board Meeting
Phase II Identify Community Needs & Desires
A. Conduct & Analyze Surveys
1.Senior Survey November
2. Conduct Citizen Survey December
3. Tabulate and analyze early Dec - Jan.
B. Conduct Visual Preferencing Study
1. Develop visuals
2. Survey
3. Analyze and share results
B. Conduct & Analyze Focus Groups
Secure $ for Graphic Renditions of Options
1. Prepare Concept Boards late Nov.
2. Conduct Focus Groups
a. Seniors
b. Town thought Leaders
c. Contractors & Realtors
d. General Public
3. Analyze and share findings
Phase III Gain Peer Insights
A. Planners and other Towns Best Practices panel
Phase IV Rewrite
A. Clean-up - e.g.. District M, typos
B. Begin Drafting housing options based on survey
C. Refine based on Focus Groups findings
D. Revenue Estimates
E. Legal Review
Phase V Outreach& Explanation
A. Develop Outreach Materials
B. Conduct Outreach Meetings
1. Board Meetings
2. COA Meetings
3. General Population
4. Contractors, Real Estate Agents
5. Other Town's Planners - peer review
C. Develop and Manage PR
1. Harvard Press/NextDoor
2. Harvard NextDoor
D. Public Hearings - pb
Phase VI Pass Bylaw
Town Meeting | [7 empty] | 2020-05-15