**OSRD PROJECT SCHEDULE 2021-22**

|  |  |  |
| --- | --- | --- |
| **OCTOBER 2021** | **Week 3** | **Week 4** |
| Create and Maintain Website (Ongoing) |  |  |
| Develop Project Dropbox |  |  |
| PB and Other Meetings (⧫) | ⧫ (10/18) |  |

**October 29, 2021** – Complete website and Dropbox folder for project.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **NOVEMBER 2021** | **Week 1** | **Week 2** | **Week 3** | **Week 4** | **Week 5** |
| Develop a 2-Pager and Q&A | 🟏 |  |  |  |  |
| Public Outreach Meeting |  |  |  |  | 🟏 |
| PB Meetings (⧫) | ⧫ (11/1) |  | ⧫ (11/15) |  |  |
| Plan and Schedule Stakeholder Mtgs. |  |  |  |  |  |
| Planner Coffee (❖) |  | ❖ |  |  |  |

**November 1, 2021** – PowerPoint Presentation on Dimensional and Design Requirements

**November 15, 2021** – PowerPoint Presentation on the Design Process; Review Drafts and Begin Critique and Editing

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **DECEMBER 2021** | **Week 1** | **Week 2** | **Week 3** | **Week 4** | **Week 5** |
| Stakeholder Focus Groups (◼) |  | ◼ |  |  |  |
| PB Meetings (⧫) | ⧫ (12/6) |  | ⧫ (12/20) |  |  |
| Board Outreach Meetings |  |  |  |  |  |
| Planner Coffee (❖) |  | ❖ |  |  |  |
| Upload Bylaw Draft on Website |  |  | ◆ |  |  |

**December 6, 2021** – PowerPoint Presentation on the Formal Application Process; Continue Draft Evaluation

**December 20, 2021** – Complete Draft Evaluation; Upload on Website

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **JANUARY 2022** | **Week 1** | **Week 2** | **Week 3** | **Week 4** |
| Board Outreach Meetings |  |  |  |  |
| PB Meetings (⧫) | ⧫ (1/3) |  | ⧫ (1/17) |  |
| Stakeholder Focus Groups |  | ◼ |  |  |
| Planner Coffee (❖) |  | ❖ |  |  |

**January 3, 2022** – Discuss Outreach Progress

**January 17, 2022** – Discuss Outreach Progress

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **FEBRUARY 2022** | **Week 1** | **Week 2** | **Week 3** | **Week 4** |
| Board Outreach Meetings |  |  |  |  |
| PB Meetings (⧫) | ⧫ (2/7) |  |  | ⧫ (2/28) |
| Stakeholder Focus Groups | ◼ |  |  |  |
| Planner Coffee (❖) |  | ❖ |  |  |

**February 7, 2022** – Open Public Hearing; Discuss Outreach Progress

**February 28, 2022** – Continue Public Hearing; Discuss Outreach Progress

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **MARCH 2022** | **Week 1** | **Week 2** | **Week 3** | **Week 4** | **Week 5** |
| Board Outreach Meetings |  |  |  |  |  |
| PB Meetings (⧫) | ⧫ (3/7) |  | ⧫ (3/21) |  |  |
| Planner Coffee (❖) |  | ❖ |  |  |  |

**March 7, 2022** – Continue Public Hearing; Discuss Outreach Progress

**March 21, 2022** – Continue Public Hearing; Discuss Outreach Progress

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **APRIL 2022** | **Week 1** | **Week 2** | **Week 3** | **Week 4** |
| PB Meetings (⧫) | ⧫ (4/4) |  |  | ⧫ (4/25) |
| Plan OSRD Open House |  |  |  |  |
| Planner Coffee (❖) |  |  |  | ❖ |

**April 4, 2022** – Continue Public Hearing; Discuss Outreach Progress

**April 25, 2022** – Continue Public Hearing; Discuss Outreach Progress

|  |  |  |
| --- | --- | --- |
| **MAY 2022** | **Week 1** | **Week 2** |
| PB Meetings (⧫) | ⧫ (5/2) |  |
| OSRD Open House | ◆ |  |
| Town Meeting |  | ◆ |

**May 2, 2022** – Close Public Hearing

**May 14, 2022** – TOWN MEETING