## Previous Mitigation Actions
Action # | Action Title | Action Description | Mitigation Goal | Mitigation Category | Hazard(s) Addressed | Estimated Cost | Potential Funding Source | Lead Department | Implementation Schedule | Priority (STAPLEE Score) | Priority | Current Status | Current Status Description/Explanation | Keep for Updated Plan? | Updated Action Title/Description (if applicable)
1 |  | Identify Existing Shelters that are Earthquake Resistant as well as Outside of Floodplain (and Dam Inundation) Areas to ensure that shelters are available to reduce or eliminate risk to human life. |  |  | Flood Related Hazards and Geologic Hazards |  | Municipal Staff | Building Commissioner, Emergency Management Director | 2015-2020 | 17 |  | Completed + To Be Continued | New Harvard Elementary School falls under current building code. | NO - explanation provided at left | #4, Updating Town Bylaws and Zoning Bylaws to prioritize hazard mitigation, climate adaptation and resiliency. Implementing this action will ensure shelters and are located appropriately.
2 |  | Increase awareness by educating property owners on actions that they can take to reduce risk to property through internet and by hosting an Open House at the Fire Department, Develop and Distribute an Educational Pamphlet on Fire Safety and Prevention (SAFE PROGRAM) (SENIOR SAFE) and wildfire prevention. |  |  | Wildland Fire |  | Municipal Staff | Fire Department | 2015-2020 | 20 |  | Completed + To Be Continued | This is an ongoing project and will continue. | YES - updated/revised description provided at right, if applicable | #21 and #22, These actions include education and outreach programs.
3 |  | Inventory Supplies at Existing Shelters and Develop a Needs List and Storage Requirements to ensure the available of adequate supplies during a natural hazard. Supplies must be adequate to eliminate or reduce risk to human life. |  |  | All Natural Hazards |  | Municipal Staff | Emergency Management Planning Committee, School Facilities Manager | 2015-2020 | 21 |  | Partially Completed / In Progress | We have all Emergency Management Equipment in a new trailer but this equipment needs to be gone through to ensure it is still good. | NO - explanation provided at left
4 |  | Identify all structures throughout the town that need to be Elevated above the Base-Flood Elevation. Once identified educate those property owners regarding their options for mitigation |  |  | Flood Related Hazards |  | Municipal Staff. Also 75% FEMA FUNDING AVAILABLE. Remaining 25% (non- federal) | Building Commissioner, Fire Department | 2015-2020 | 21 |  | Delayed | Now that we have a new building commissioner the Fire Department can work with him to complete this task | YES - updated/revised description provided at right, if applicable | #14 and #15, These actions include adopting the 202 MA State Model Floodplain Bylaw, identifying a Floodplain Administrator, and expanding the Town's capacity to mitigate flood risk. Actions # 21 and 22 include education and outreach.
5 |  | To develop a priority list and possibly seek funding through the Hazard Mitigation Grant Program (HMGP) for the replacement of undersized culverts throughout Town to reduce or eliminate flooding risk. |  |  | Flood Related Hazards |  | Municipal Staff/ FEMA HMGP grant 75% MEMA/ FEMA | Board of Selectmen, Highway Department | 2015-2020 | 21 |  | Delayed | It is necessary to continue this action. | YES - updated/revised description provided at right, if applicable | Action #12, Replace culverts based on need.
6 |  | Educate property owners regarding options for mitigating their properties from flooding through outreach programs that address measures that residents can take ( i.e. installing backflow valves, securing debris, etc.) |  |  | Flood Related Hazards |  | Municipal Staff/ Property Owners | Emergency Management Director, Fire Department | 2015-2020 | 21 |  | Partially Completed / In Progress | Have provided links to FEMA through our website that addresses these issues. However, lack of time from personnel has delayed us on pursuing outreach programs to address this. | YES - updated/revised description provided at right, if applicable | #21 and #22, These actions include education and outreach programs.
7 |  | Continue participation in the National Flood Insurance Program to enable property owners to purchase insurance protection against flood losses. |  |  | Flood Related Hazards |  | FEMA/ MEMA | Board of Selectmen, Conservation Commission | 2015-2020 | 21 |  | Partially Completed / In Progress | Harvard participates in the NFIP but is interested in expanding compliance and implementation. | YES - updated/revised description provided at right, if applicable | #14 and #15, These actions include adopting the 202 MA State Model Floodplain Bylaw, identifying a Floodplain Administrator, and expanding the Town's capacity to mitigate flood risk. Actions # 21 and 22 include education and outreach.
8 |  | Enforce state building codes related to design loads to include wind effects generated from atmospheric related hazards. |  |  | Atmospheric Related Hazards |  | Contractor and Property Owners | Building Commissioner, Emergency Management Director | 2015-2020 | 21 |  | Partially Completed / In Progress | This action needs to continue with education and enforcement. | YES - updated/revised description provided at right, if applicable | Action #2, Enforce state building codes.
9 |  | Identify areas with potential for brush fires to track community vulnerability by developing and maintaining a data base. |  |  | Wildland Fire |  | Municipal Staff | Department of Public Works | 2015-2020 | 21 |  | Partially Completed / In Progress | This action needs to continue with brush clearing, fire breaks, and fire ponds. | YES - updated/revised description provided at right, if applicable | Action #16, Identify areas prone to brush fires and mitigate this risk with brush clearing, building fire breaks, and maintaining fire ponds or cisterns.
10 |  | Utilize interactive mapping application prepared by MRPC/CMRPC to update critical infrastructure and simulate real time evacuation scenarios to mitigate hazards to the public. |  |  | All Natural Hazards |  | Emergency Management Director with MRPC | Emergency Management Director | 2015 | 21 |  | Partially Completed / In Progress | We have updated the critical infrastructure list but have not done anything else. | YES - updated/revised description provided at right, if applicable | Action #8, Expand GIS capacity to support hazard mitigation and climate adaptation efforts.
11 |  | Maintain "beaver diverters" and water control devices to mitigate flooding. |  |  | Flood Related Hazards |  | Municipal Staff | Department of Public Works | 2015-2020 | 21 |  | Partially Completed / In Progress | Beavers continue to pose a threat. | YES - updated/revised description provided at right, if applicable | Action #13, Install and maintain beaver management devices to mitigate flood risk.
12 |  | Implement recommendations regarding natural hazard mitigation in existing planning documents including the master plan, five year action plan of the open space and recreation plan and the emergency evacuation plan |  |  | All Natural Hazards |  | Municipal Staff, Conservation Commission, Board of Selectmen, Planning Board, Emergency Management Director | Conservation Commission, Board of Selectmen, Planning Board, Emergency Management Director | 2015-2020 | 21 |  | Partially Completed / In Progress | This is an ongoing action and is reflected in the MVP. | YES - updated/revised description provided at right, if applicable | This action is reflected in multiple actions in the 2022 plan. Including #3 Develop a Climate Adaptation Plan that is consistent with the Hazard Mitigation Plan and MVP.
13 |  | Establish Asset Management Inventory and Condition Database and Management Plan to ensure that vital equipment needed for hazards is in working condition to mitigate natural hazards. |  |  | All Natural Hazards |  | Municipal Staff | Department of Public Works | 2018 (12 months) | 21 |  | Cancelled | This action is not relevant. | NO - explanation provided at left

## MVP Recommendations
Number | MVP Recommendation | Notes / Comments | 2022 Hazard Mitigation Plan Relevance
Highest Priority
1 | Create an implementation committee to manage the process of creating and monitor implementation of a comprehensive Climate Action Plan that would include, at minimum, the following planning modules: - A town-wide tree/forest management plan that would address trees on public lands and public rights-of-way - Land stewardship plan - Invasive species planning - An agricultural action plan - Coordinate emergency management planning with climate change vulnerabilities that includes vulnerable populations and road system interconnectivity | This plan is under development. | Action #3, Develop a Climate Adaptation Plan that is consistent with the Hazard Mitigation Plan and MVP.
2 | Establish a Climate Vulnerability Liaison within Town government responsible for capital planning oversight. | Not realistic.
3 | Create an emergency response network and a medical professional network to coordinate professional and volunteer-based emergency and medical response teams. This combined network should include Town public safety departments (police, fire, Board of Health, Council on Aging, DPW), existing or new CERTs (Civilian Emergency Response Teams), and existing volunteer organizations, such as Harvard’s Snowmobile Club. | This is relevant. | Action #7, Develop a Medical Reserve Corps.
High Priority
4 | Establish and equip The Bromfield School as a stay-over shelter with a prepared management plan. Establish and equip Hildreth House as a cooling and warming shelter with amenities like phone charging and hot coffee. | It does not make sense to equip the Hildreth House. This action has been revised. | Action #9 includes adding a generator to the Elementary School so it can function as a heating and cooling center.
5 | Add more alternative power sources (generators and batteries) to all municipal buildings. |  | Action #9 includes adding a generator to the Elementary School and the new Council on Aging facility so they can function as a heating and cooling center.
6 | Strengthen the Town’s website for cross-cultural communication, preparation, and coordination. |  | Action #11 prioritizes vulnerable populations, and Actions 21 and 22 include education and outreach.
7 | Provide opportunities for cross-cultural exchanges to connect disparate groups. Implement public awareness and education programming pertaining to farm success planning. |  | Action #11 prioritizes vulnerable populations, and Actions 21 and 22 include education and outreach.
8 | Monitor, manage, maintain, and preserve public lands. Educate private land-owners on best practices for collective stewardship. |  | Action #6 includes land protection. Actions 21 and 22 include education and outreach.
9 | Remove invasive plant species from conservation lands and plant native species where ecological edges and buffer zones have been disturbed. |  | Action #10 calls for the removal of invasive species.
10 | Provide education in systems-thinking and stewardship (i.e., fertilizers and ecological buffers.) |  | Actions 21 and 22 include education and outreach.
11 | Create and implement a comprehensive regional strategy for land stewardship including best practices for bittersweet removal and deer fencing. |  | Action #10 calls for the removal of invasive species.
12 | Support the “Pond Committee” who oversees the monitoring and management of Bare Hill Pond. |  | Action #1 includes flood control, algae blooms and pond biodiversity as well as eduction. Action #6 includes water quality protection, Action #10 includes removing invasive plant species from conservation land.
13 | Continue and support the work of the Board of Health which provides educational programming pertaining to public health and disease control including tick control methods. |  | Actions 21 and 22 include education and outreach.
14 | Provide educational programming on pollinators and pollinator habitat and the impacts of spraying for ticks and mosquitoes on pollinator species. |  | Actions 21 and 22 include education and outreach.
Moderate Priority
16 | Evaluate, design, expand, and upgrade the culvert system and maintain a budget for emergency repairs and replacements. | To me this should be a higher priority re. flooding and why we are going after grants for this. | Action #12 includes replacing culverts as needed.
17 | Evaluate, plan, and implement an expanded storm-water detention system and maintain a budget for emergency repairs and replacements. |  | Action #20 relates to stormwater management.
18 | Adopt a by-law and seek funding for town-wide evaluation and recommendations for improving drainage and storm-water management.
19 | Plan for expanded emergency response capacity. Improve facilities and implement plans to coordinate the department of public works, fire, and EMT. | Not sure I understand this one.
20 | Tamper roads to create crowns for water run-off.
21 | Implement vegetative buffers along roadsides. |  | Action #10 implements vegetative buffers.
22 | Improve erosion control. | Have we done this with the by law change voted at the last town meeting. | Action #10 implements vegetative buffers.
23 | Create a shared information base to foster better community understanding. | ? Not sure what this means. | Actions 21 and 22 include education and outreach.
24 | Provide educational programming on invasive species. |  | Actions 21 and 22 include education and outreach.
25 | Create, identify, and coordinate a “metagroup” of community groups and neighborhood organizations for improved cross-cultural communication. | Not sure I understand this one . When it comes to addressing preparedness, I would like to see community organization around knowing neighbors, check-up system during storms, etc.
26 | Provide education and monitor the proper disposal or conservation of older trees. |  | Actions 21 and 22 include education and outreach.
27 | Monitor Bare Hill Pond for algae blooms. Improve and expand infrastructure as needed. |  | Action #1 mentions alagal boolms and monitoring water.
28 | Provide educational programming on the rhododendron threat, soil health, integrated pest management (IPM), and inter-planting (planting companion plantings to maximize land use, reduce the impacts of disease and pests, and improve soil health). | I have no idea what the threat is. Is it more than just one plant. | Actions 21 and 22 include education and outreach.
Lower Priority
29 | Evaluate road conditions and secure funding as needed to improve infrastructural resilience. |  | Action #12 includes replacing culverts as needed.
30 | Evaluate private septic systems to identify problematic locations. Evaluate the vulnerabilities, advantages, and funding needed to expand the Town sewer system. |  | Action #6 addresses water protection including wells.
31 | Maintain a budget for shelter supplies. | Shouldn't this be a higher priority. Supplies need to be readily available. Otherwise like covid response - lack of supplies
32 | Collate strategies for hazards pertaining to settlement patterns in small New England towns.
33 | Evaluate and improve road connectivity and redundancies through systems planning.
34 | Include Devens’ vulnerable populations in planning efforts. |  | Devens was not directly addressed via mitigation actions.
35 | Assess and create a plan to connect all vulnerable populations to coordinate emergency response. | Why isn't this higher | Action #11 prioritizes mitigating risk to vulnerable populations.
36 | Create and implement a Land Stewardship/Bare Hill Pond and Watershed Plan.
37 | Improve erosion control through use of silt fencing and hay bales; establish a bylaw to enforce. |  | Action #4 addresses Town Bylaws and Zoning Bylaws. Action #6 addresses water quality and land protection.
38 | Test wells and water sources for contamination, educate the public about risks and best practices for management. Prioritize land around wetlands, ecological buffers, and groundwater resources. |  | Action #6 focuses on water quality and testing. Actions 21 and 22 include education and outreach.
39 | Aid the Harvard Conservation Trust and the Sudbury Valley Trustees in conserving more land and implementing more public outreach and education. | This should be higher for climate action plan thought not a hazard plan
40 | Build aquifer cisterns and fire ponds. |  | Action #16 includes fire protection cisterns and fire ponds.
41 | Provide educational programming pertaining to crops and farming in Harvard. Topics to include adjusting crops to the growing season, using Hoop Houses (greenhouses), transitioning to more southern varieties of apples, using nutrient sprays such as Manganese to improve calcium uptake, micro-nutrients, raised plant beds, and smudge pots to prevent frost on small farms. |  | Actions 21 and 22 include education and outreach.
42 | Create a community water bank and appoint an agricultural liaison for expert consultations.

## thoughts from a resident
1. Consider /Reconsider extending the town’s sewer district to residents further out from town. We came across a recent article* from the Washington Post about climate change wreaking havoc on septic systems & the changing conditions which challenge the assumptions those systems were designed with. Given Harvard’s high water table, it seems it might be a challenge for most residents in this town, eventually. The article mentions that one potential approach is to tie into a public sewer system, which is something we’ve been wondering about anyway. Is there a chance there are any plans to potentially expand Harvard’s sewer district, and extend the option to tie in to homes & buildings further out from the town center ? Has this been considered recently?
*Here is the article which sparked our family’s conversation about this:
https://www.washingtonpost.com/climate-environment/2022/04/12/backed-up-pipes-stinky-yards-climate-change-is-wrecking-septic-tanks/
2. Consider expanding the town’s management and/or help with identification & mitigation of sick and stressed trees. There seems to be increasing damage from invasive pests, and effects of prior drought which seem to be affecting many trees; and those conditions appear to potentially worsen over time.
While walking along town roads, we see a lot of near-dead but very large trees lining main roads such as Bolton Rd, which seem like an accident waiting to happen. We also heard about the tragic tree-falling accident a few years ago, which took the life of a young resident (Jessica P, “Have a Jessie Day” memorial events) , and don’t know anything beyond the archive article in the Harvard Press, which mentioned the tree appeared healthy & snapped.
We wonder if some future tragic accidents could be avoided, with a careful town-funded /subsidized examination of trees that might be unhealthy despite initial appearances (& a danger to people, homes , electrical wires, and those traveling on roads), with some help to address high-priority issues in anticipated stressful conditions, before big limbs or trunks snap & fall where they may.
3. Fund and facilitate, and publicize additional local incentives to incorporate solar power into their homes & properties (and any highly efficient fuel alternatives), to help pick up the pace of reducing dependency on fossil fuels. We heard about the recently expired HeatSmart program, which seemed to make a big difference at the homes of a number of community members. Also, add solar panels to more public buildings (like on HES) & available public grounds, as a matter of course moving forward & ideally retrofitting any eligible high-impact existing buildings, too. They could become educational sites as well as productive ones. Perhaps artists could get involved to help beautify areas or corridors used this way, similar to artwork exhibits or murals on community rail trails.
4. Encourage & subsidize community-coordinated plantings , to help with climate change one backyard / front yard / school yard at a time. Inspired by the research and work of ecologists, who make a data-driven & empowering case for the positive impact communities and homeowners can make to mitigate climate change issues. (See for example this book by Douglas Tallamy, available at our library:
https://harvard.cwmars.org/eg/opac/record/4482004?query=Natures%20best%20hope%20 ) They provide highly localized plant lists , and members of Harvard’s Garden Club could likely be engaged to help.
5. Equip (and/or educate & enable) residents and public buildings with hyper-local emergency kits & plans, at least at a community level, addressing the most anticipated localized issues. (Eg in CA they were mainly Earthquake kits, or Wildfire “go bags”) It’s never fun to think about, but could be done well. (Eg not as much the focus in MA, but see “The Great Shakeout” community-wide earthquake drills
https://www.shakeout.org and
https://www.usgs.gov/news/featured-story/shakeout-2021-earthquake-awareness-enables-community-preparedness)
DPW: “Applied for DER culvert grant on March 14, 2022 for data gathering and design costs for a culvert on Scott Rd.”

## 2022 Actions
# | Goal Category | Type of Mitigation Action | Hazard Addressed | Action | Action Description | Critical Facility | Estimated Cost | Potential Funding Source | Lead Department | Supporting Partners & Departments | Implementation Schedule | Priority | Social | Technical | Administrative | Political | Legal | Economic | Environmental | STAPLEE Score |  | Flood | Landslide | Wildfires and Brushfires | Hurricanes and Wind | Severe Winter Storms | Tornadoes | Thunderstorms | Earthquakes | Drought | Extreme Temperatures | Infectious Disease | Invasive Species
1 | Capacity Building and Planning | Natural Systems Protection | Flooding, Public Health, Invasive Species | Implement down-stream flood control and monitor for water health, algae blooms, and biodiversity of pond. Provide education and outreach to the public regarding these issues. | • Hire scientific/technical consultant to monitor water, implement mitigation actions to address algal blooms. Update the Land Stewardship/Bare Hill Pond Watershed Management Plan. • Algae blooms impact water-related activities and the health of the environment. Educating the community and expanding infrastructure may prevent algae blooms and their impact. | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Bare Hill Pond Watershed Management Committee | Board of Health, DPW, Conservation Commission | 1-5 Years | High | 3 | 3 | 2 | 3 | 3 | 2 | 3 | 19 | Benefits Exceed Costs | Yes | [10 empty] | Yes
2 | Critical Facilities and Infrastructure | Local Plans and Regulations | Flood | Catalog all permitted BMP's (stormwater control measures) to develop compliance procedures to maintain stormwater storage capacity. |  | Yes | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Conservation Commission |  | 3 Years | High | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 19 |  | Yes |  |  |  | Yes |  | Yes
3 | Capacity Building and Planning | Local Plans and Regulations | High Winds | Enforce state building codes. | To mitigate potential risks from atmospheric hazards generating strong winds, the Town will enforce MA State Building Codes related to design loads. Provide continuing education for the Building Commissioner. | Yes | Low under $20,000 | FEMA or Town Meeting grants a Project and then a Warrant Article for Funding | Building Commissioner | Commission on Disabilities, Permanent Building Committee | 1-5 Years | High | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 18 | Benefits Equal Costs | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
4 | Capacity Building and Planning | Local Plans and Regulations | All Hazards | Be aggressive and creative regarding the pursuit of funding for hazard mitigation and climate action goals. This should include community-centered and regional opportunities to address local and regional hazard risk reduction projects. | • Pursue MVP Action Grants and other grants with neighboring communities. • Leverage opportunities with other sources, such as the Town’s Capital Planning and Investment Committee, to help fund priority hazard mitigation and climate adaptation projects, particularly when combined with alternative/external grant funding sources when a local cost-share increases the Town’s chances for a grant award. | No | Low under $20,000 | MVP, FEMA, EPA Sewer Overflow and Stormwater Reuse Municipal Grant Program | Harvard Climate Initiative Committee and Emergency Management | Harvard Climate Initiative Committee | 1-5 Years | High | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 18 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
5 | Capacity Building and Planning | Local Plans and Regulations | All Hazards | Develop a Climate Adaptation Plan that is consistent with the Hazard Mitigation Plan and MVP. | Develop a Climate Adaptation Plan that includes mitigation actions and is consistent with the mitigation strategy. This plan should emphasize community education and opportunities for residents to support the Town's sustainability and resiliency. | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Harvard Climate Initiative Committee | Harvard Climate Initiative Committee Partners | 1 Year | High | 3 | 3 | 2 | 2 | 3 | 2 | 3 | 18 | Costs Exceed Benefits | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
6 | Capacity Building and Planning | Local Plans and Regulations | All Hazards | Update Town Bylaws and Zoning Bylaws to prioritize hazard mitigation, climate adaptation and resiliency. | Incorporate Nature-based Solutions (NbS) into Town Bylaws. Update Zoning Bylaws through a series of amendments related to hazard mitigation, climate adaptation, and overall environmental sustainability. Publicize and promote effectiveness of NbS through a demonstration site and outreach materials. | No | Medium $20,000-$100,000 | MVP | Planning Board and Harvard Climate Initiative Committee | Harvard Climate Initiative Committee, Conservation Commission | 2 Years | High | 2 | 3 | 3 | 2 | 3 | 2 | 3 | 18 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
7 | Critical Facilities and Infrastructure | Natural Systems Protection | Flooding, Public Health, Invasive Species | Implement a plan of ongoing water quality protection through continuing the regular testing of wells and other water sources. Maintain and enhance robust land protection around wetlands, ecological buffers, and groundwater sources, as applicable. | • The Town shall continue the diligent testing of well water quality and address issues in a timely manner as they arise. Consider connectivity to Devens system for Center and Ayer Road. • Revise and update land protection regulations and bylaws as necessary. | No | Medium $20,000-$100,000 | MVP | Planning Board, Conservation Agent, Water Commission, Board of Health | Department of Public Works | 3 Years | High | 3 | 2 | 2 | 3 | 3 | 2 | 3 | 18 |  | Yes | [7 empty] | Yes | Yes | Yes
8 | Capacity Building and Planning | Local Plans and Regulations | All Hazards | Develop a Medical Reserve Corps. | Create an emergency response network and a medical professional network to coordinate professional and volunteer-based emergency and medical response teams. This combined network should include Town public safety departments (police, fire, Board of Health, Council on Aging, DPW), existing or new CERTs (Civilian Emergency Response Teams), and existing volunteer organizations, such as Harvard’s Snowmobile Club. | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Emergency Management & Police Department | Department of Public Works, Harvard School Committee, Board of Health, Council on Aging | 3-5 Years | High | 3 | 3 | 2 | 3 | 3 | 3 | 1 | 18 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
9 | Critical Facilities and Infrastructure | Natural Systems Protection | Invasive Species | Remove invasive plant species from conservation lands and plant native species where ecological edges and buffer zones have been disturbed. Implement vegetative buffers along roadsides. |  | No | High over $100,000 | MVP | Conservation Commission | Garden Club | 1-5 Years | High | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 17 | [12 empty] | Yes
10 | Capacity Building and Planning | Local Plans and Regulations | All Hazards | Expand GIS capacity to support hazard mitigation and climate adaptation planning efforts. | Develop GIS data and maps relevant to agriculture (local farms in Harvard) to assist with future geospatial analysis in support of hazard mitigation and climate adaptation planning efforts. | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Town Administrator |  | 2 Years | High | 3 | 2 | 3 | 3 | 3 | 1 | 2 | 17 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
11 | Critical Facilities and Infrastructure | Structure and Infrastructure Projects | All Hazards | Add back-up power to the Town Hall. |  | Yes | Medium $20,000-$100,000 | FEMA HMGP or BRIC | Emergency Management | Town Administrator, Harvard School Committee | 2 Years | High | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 17 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
12 | Critical Facilities and Infrastructure | Structure and Infrastructure Projects | All Hazards | Add a generator to the new Council on Aging facility and formalize the Elementary School as a cooling or warming center. |  | Yes | Medium $20,000-$100,000 | FEMA HMGP or BRIC | Emergency Management | Town Administrator, Harvard School Committee | 2 Years | High | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 17 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
13 | Capacity Building and Planning | Local Plans and Regulations | All Hazards | Prioritize vulnerable populations in Harvard when mitigating natural hazard risks and climate adaptation measures. | In order to effectively mitigate risk to vulnerable populations the Town must understand their locations and needs. | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Council on Aging | Fire Department/Police Department | 1-5 Years | High | 3 | 2 | 2 | 3 | 3 | 2 | 1 | 16 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
14 | Critical Facilities and Infrastructure | Structure and Infrastructure Projects | Flood | Replace culverts based on need. | Develop a list of town-owned culverts, including those identified in the Apple Country and MVP reports, and rank them to prioritize those that need to be replaced or upgraded to mitigate flood risk. The DPW applied for a DER culvert grant on March 14, 2022 for data gathering and design costs for a culvert on Scott Rd. | No | Medium $20,000-$100,000 | MA DER Culvert Replacement Municipal Assistance Grant Program, FEMA BRIC or HMGP, MVP | DPW | Floodplain Administrator | 1-5 Years | High | 3 | 2 | 2 | 2 | 3 | 1 | 3 | 16 |  | Yes |  |  | Yes | Yes | Yes | Yes
15 | Critical Facilities and Infrastructure | Natural Systems Protection | Flood | Install and maintain beaver management devices to mitigate flooding risk. |  | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Conservation Commission & DPW | Department of Public Works | 1-5 Years | High | 3 | 2 | 2 | 3 | 3 | 1 | 2 | 16 |  | Yes |  |  | Yes | Yes | Yes | Yes
16 | Critical Facilities and Infrastructure | Natural Systems Protection | Wildfire | Identify areas prone to brush fires and mitigate this risk with brush clearing, building fire breaks, and maintaining fire ponds or cisterns. |  | No | Medium $20,000-$100,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Fire Department | GIS Manager | 1-5 Years | Medium | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 15 |  |  |  | Yes
17 | Critical Facilities and Infrastructure | Structure and Infrastructure Projects | High Winds | Expand the Town's management of trees by routinely examining trees, trimming or removing unhealthy trees, and educating the public about tree health. | Invasive species, drought, and climate change are damaging trees which increases the risk of trees toppling during storms. Educate homeowners how to be aware of sick trees on their properties. | No | Medium $20,000-$100,000 | National Grid, Town Meeting grants a Project and then a Warrant Article for Funding | Tree Warden & Elm Commission | Department of Public Works, National Grid | 1-5 Years | Medium | 3 | 2 | 2 | 2 | 3 | 1 | 2 | 15 |  |  |  |  | Yes | Yes | Yes | Yes
18 | Capacity Building and Planning | Local Plans and Regulations | Flooding, Extreme Weather | Expand capacity to mitigate flood risk and support the National Flood Insurance Program (NFIP) by formally designating a community Floodplain Administrator (FPA), supporting the FPA to be certified as a Certified Floodplain Manager (CFM). | This includes designating departments/positions with specific NFIP-related roles and responsibilities, and linking those staff with proper training and educational opportunities. | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Town Planner | Harvard Climate Initiative Committee, Conservation Commission, Building Commissioner/Facilities Manager | 1 Year | Medium | 2 | 3 | 1 | 2 | 3 | 2 | 2 | 15 |  | Yes |  |  | Yes | Yes | Yes | Yes
19 | Capacity Building and Planning | Local Plans and Regulations | Flooding | Adopt the 2020 MA State Model Floodplain Bylaw. | Adopt the 2020 MA State Model Floodplain Bylaw to assure that the Town’s current bylaws and ordinances (Zoning Bylaw Chapter 125-54) contain the necessary and proper language for compliance with the NFIP and state requirements. | No | Low under $20,000 | MVP | Planning Board | Building Commissioner/Facilities Manager, Floodplain Administrator | 2 Years | Medium | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 15 |  | Yes |  |  | Yes | Yes | Yes | Yes
20 | Capacity Building and Planning | Local Plans and Regulations | All Hazards | Fill vacant staff positions and increase positions to support implementation of mitigation actions and climate adaptation. | Fill Community and Economic Development Director Position, add a Sustainability Coordinator position, add hours for the Board of Health staff, add additional DPW personnel, and support for the Building Commissioner. | No | High over $100,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Select Board & Town Administrator | Conservation Commission, Board of Health, Harbormaster | 4 Years | Medium | 1 | 3 | 2 | 1 | 3 | 1 | 3 | 14 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
21 | Critical Facilities and Infrastructure | Structure and Infrastructure Projects | All Hazards | Establish energy resilience for public buildings and other critical facilities by installing solar panels or other renewable source and add back-up power, as funding opportunities arise. | • Solar and other renewables add a self-sufficiency factor to critical facilities and infrastructure and reduce risk. • Backup battery power further reduces the risk and adds needed redundancy. | Yes | High over $100,000 | FEMA HMGP or BRIC | Permanent Building Committee and Energy Committee | Building Commission/Facilities Manager, Fire Department/Emergency Management | 4 Years | Medium | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 14 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
22 | Critical Facilities and Infrastructure | Structure and Infrastructure Projects | Flooding, Hurricanes/Tropical Storms, Severe Winter Storm/Nor'easter, tornadoes, Other Severe Weather | Evaluate, plan, and implement an expanded stormwater detention system, purchase additional equipment for drainage, and maintain a budget for emergency repairs and replacements. |  | Yes | High over $100,000 | FEMA BRIC, HMGP or MVP | Department of Public Works and CFM |  | 3 Years | Low | 2 | 1 | 2 | 2 | 3 | 1 | 2 | 13 |  | Yes |  |  | Yes | Yes | Yes | Yes
23 | Public Education and Outreach | Education and Awareness Programs | All Hazards | Update and maintain the Town managed websites with hazard mitigation and climate adaptation information. | • Websites should include information regarding hazard mitigation, disaster preparedness, disaster response and recovery. Use the following websites at a minimum, Town, Harvard Climate Initiative Committee, BOH, COA, and Fire Departments. • To facilitate implementation and maintenance as well as public awareness, the Town may wish to integrate plans (HMP, MVP, Master Plan and other resilience-themed plans/reports) into a consolidated document and/or topic website, to facilitate their implementation and maintenance. | No | Low under $20,000 | Town Meeting grants a Project and then a Warrant Article for Funding | Town Administrator |  | 5 Years | Low | 2 | 2 | 2 | 1 | 3 | 1 | 2 | 13 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
24 | Public Education and Outreach | Education and Awareness Programs | All Hazards | Develop a robust education program for residents and business owners that includes all natural hazards, climate adaptation, and hazard mitigation. | Educate property owners about how to mitigate risk to their properties such as installing backflow valves, removing debris, installing solar power, and disposing of older trees. | No | Low under $20,000 | FEMA BRIC, HMGP or MVP | Emergency Management and Harvard Climate Initiative Committee | Harvard Climate Initiative Committee | 1-5 Years | Low | 2 | 1 | 2 | 1 | 3 | 1 | 2 | 12 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Key to Participants
1 - Town Administration
2 - Select Board
3 - DPW
4 - Fire Department/Emergency Management
5 - Police Department
6 - Harvard Climate Initiative Committee (Harvard Climate Initiative Committee)
7 - Harvard School Committee
8 - Harvard Town Meeting
9 - Planning Board
10 - Conservation Commission
11 - Board of Health
12 - Harbormaster
13 - Bare Hill Pond Watershed Management Committee
14 - Agriculture Advisory Commission
15 - Commission on Disabilities
16 - Council on Aging
17 - Permanent Building Committee
18 - Transportation Advisory Committee
19 - Water & Sewer Commission
20 - Tree Warden
21 - Devens Enterprise Commission
22 - Building Commissioner/Facilities Manager
23 - Capital Planning and Investment Committee
24 - Floodplain Administrator (FPA)
25 - GIS Manager
26 - Parks & Recreation Commission
27 - Harvard Conservation Trust

## Dropdown Lists (hidden)
Mitigation Goals
TBD
TBD
TBD
TBD
TBD
Mitigation Category
Local Plans & Regulations
Structure & Infrastructure Projects
Natural Systems Protection
Education & Awareness Programs
Emergency Preparedness
Priority
Very High
High
Medium
Low
Project Status
Completed
Completed + To Be Continued
Partially Completed / In Progress
Delayed
Cancelled
Keep for Updated Plan?
YES - updated/revised description provided at right, if applicable
NO - explanation provided at left